## Sheet1
Task description | Team member | Date assigned | Date finished
Entity Relationship Diagram | All | 2021-03-14 | 2021-03-14
Entity Relationship Diagram - revision | Jerome | 2021-03-14 | 2021-03-16
Entity Relationship Diagram - revision 2 | Kyung | 2021-03-25 | 2021-03-25
Database schema | Jerome | 2021-03-15 | 2021-03-16
Database schema - revision | Kyung | 2021-03-25 | 2021-03-25
Create GCP Project and SQL instance | Taimoor | 2021-03-25 | 2021-03-25
Intialize database | Taimoor | 2021-03-25 | 2021-03-25
Creation of initial dummy data | Jerome | 2021-03-14 | 2021-03-20
Import dummy data into SQL instance | Taimoor | 2021-03-25 | 2021-03-25
Sketches of UI | Kyung | 2021-03-25 | 2021-03-25
Initialize Django project | Jerome | 2021-03-25 | 2021-03-25
Connect front-end with database | All | 2021-03-25 | 2021-03-26
Decide on transactions | Kyung |  | 2021-04-21
Defined ORM mapping for all tables - Guest | Jerome/Taimoor |  | 2021-05-05
Defined ORM mapping for all tables - Employee | Jerome |  | 2021-05-05
Apply transactions to make reservations | Jerome |  | 2021-05-05
Apply transactions to employee | Jerome |  | 2021-05-05
Add functionality to delete reservation | Jerome/Taimoor |  | 2021-05-05
Built indexes for reservation and room tables | Jerome/Taimoor |  | 2021-05-05
Created Indexes for Attributes | Jerome/Taimoor |  | 2021-05-05
Added Sign in/ Register Functionality | Taimoor |  | 2021-05-05
Fetched reservations for that guest - Guest | Jerome/Taimoor |  | 2021-05-05
added functionality to add reservation - guest | Jerome/Taimoor |  | 2021-05-05
displayed updated reservations for that guest | Jerome/Taimoor |  | 2021-05-05
Added stored procedures for updating database | Taimoor |  | 2021-05-05
refined database schema iteratively | Taimoor/Kyung/Jerome |  | 2021-05-05